## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Initial Project Setup | 2 | 2024-10-05 | Set up Flutter project, configured theme, assets, and fonts to align with project requirements.
Routing & Splash Screen | 2 | 2024-10-05 | Implemented routing system and created a splash screen as per design guidelines, ensuring a smooth user entry.
UI Custom Components | 3 | 2024-10-06 | Added reusable AppBar, BottomNavigationBar, custom icons, and integrated HouseTile widget to create a cohesive design.
Overview Screen Data Fetch | 3 | 2024-10-06 | Integrated house data API and implemented a provider with Riverpod to fetch and display house data on the Overview screen.
Search Functionality | 2 | 2024-10-07 | Developed and integrated a custom search widget with conditional UI on the Overview screen to enhance user experience.
About Screen | 1 | 2024-10-07 | Created an About screen with text and link functionality, providing additional information for users.
HouseTile UI Update | 1 | 2024-10-07 | Updated the HouseTile component design to match the UI guidelines, refactoring code to improve readability and maintainability.
House Detail Screen | 3 | 2024-10-08 | Developed the HouseDetail screen with UI elements and maps integration to display property location.
Distance Calculation | 2 | 2024-10-08 | Implemented feature to calculate and display distance from user’s location after permission, ensuring accurate and dynamic UI updates.
Wishlist Feature UI | 3 | 2024-10-09 | Designed and implemented the Wishlist screen UI, allowing users to like houses and view them in a dynamic wishlist. | x
Bottom Nav updates | 1 | 2024-10-09 | Added Wishlist screen to the BottomNavigationBar and integrated a shadow effect to improve navigation visibility and aesthetics.
Final Testing & Adjustments | 2 | 2024-10-10 | Conducted comprehensive testing, verified API integration, and refined UI consistency to ensure a polished and user-friendly application.
Updating Maps | 0.5 | 2024-10-12 | Update the LocationMap widget to be able to intercept taps and route to google maps on web
Total amount of hours | 22.5